## Cover
Status | Counts | Remark | Category | Bugs | Remarks
New | 0 | Just check requirement and add to tracking list | Trade Finance | 64
On-Going | 0 |  | Credit | 9
Fixed | 22 | Committed to SVN | Transfer | 0
Delivered | 35 | Will werify on testing site when it is delivered | Teller | 0
Closed | 7 | Client tested and confirmed for close | Treasury | 0
Not Reproducible | 0 | Issue on testing site, it is working fine on Dev | Report | 0
Not Start | 1 |  |  | 0
On-Hold | 1 | Waiting for detail
Partial Fixed | 0

## Sheet1
BugNo | Category | Title | Description | Type | Severiry | Asignee | Start Date | End Date | Status | Path | Remark
Bug1 | Trade Finance | Tab MT410/field 21 is not updated automatic from Main/Field2.4 | Import\Documentary Collections\Register Phải tự động lấy giá trị ở Tab Main/field 2.4 | Bug | C-Minor | Nghia |  |  | Fixed | Logs | Verified on site, it is working fine
Bug2 | Trade Finance | Route của giao dịch Số tiền bằng chữ |  | Bug |  |  |  |  | Closed |  | anh Nguyen se check voi client
Bug3 | Trade Finance | Tất cả bảng hiện thị danh sách giao dịch | Import\Documentary Collections Không thấy dữ liệu từ trang 2 trở đi | Bug |  |  |  |  | Closed |  | Cannnot reproduce issue, aNguyen will recheck
Bug4 | Trade Finance | MT412 | Import\Documentary Collections\Accept ngày maturity date xuat file điện 412 không đúng (hiện tại field này lấy ngày khai báo giao dịch thay vì lấy ngày maturity mới đúng) | Bug | C-Minor | Nghia |  |  | Fixed | Logs | Verified, It is working fine Need to check in code if the value is correct or not then confirm
Bug5 | Trade Finance | MT412 và MT410 | Import\Documentary Collections\Accept Import\Documentary Collections\Register Khi soan dien 412 o chuc nang accept, F72 nhap thong tin /CABLE CHARGE/USD27.5 => Dien xuat ra hoan toan phu hop Nhung khi quay lai in dien 410 o chuc nang register, F72 cung cap nhat lai /CABL CHARGE/ thay vi dung la WE ACKNOWLEDGE… nhu minh da nhap luc dau | Bug | B-Major | Nghia | 2015-06-24 | 2015-06-24 | Delivered |  | [24-June-2015] TF-15097-00080 Add BDOCUMETARYCOLLECTIONMT412 and related script DocumetaryCollection Trunks_Table_TradingFinanceScript.sql Trunks_Store_TradingFinanceScript.sql
Bug6 | Trade Finance | Không thấy dữ liệu từ trang 2 trở đi | Import\Documentary Credit\Processing\Sttlement\ http://vietvictory.ddns.net/corebanking_int Tất cả bảng hiện thị danh sách giao dịch | Bug | C-Minor | Nghia | 2015-06-24 | 2015-06-24 | Delivered |  | PaymentList.ascx
Bug7 | Trade Finance | Tab 32B | Export/DocumentCredit/Advising LC Đã có dấu (*) nhưng không nhập số tiền vẫn commit được giao dịch | Bug | C-Minor | Nghia | 2015-06-24 | 2015-06-24 | Delivered |  | AdvisingAndNegotiationLC
Bug8 | Trade Finance | Tab Charge/Party Charged, bo sung A,BC | Export/DocumentCredit/Advising LC | SCR |  | Nghia | 2015-06-24 | 2015-06-24 | Delivered |  | AdvisingAndNegotiationLC
Bug9 | Trade Finance | Màn hình tiềm kiếm giao dịch | Doi ten cot "Export LC code" thanh Ref No. Doi ten cot "Ref No." thanh LC No => Du lieu tai 02 cot nay khong doi" | Bug | C-Minor |  |  |  | Delivered |  | EnquiryLC It is already changed in code. Need to publish to server
Bug10 | Trade Finance | Thư thông báo | Dòng tiêu đề: VIET VICTORY BANK ADDRESS – TEL – SWIFT => anhghi rõ như sau: VIET VICTORY BANK Floor 9, No.10, Pho Quang Str., Tan Binh Dist., HCMC Tel: 08.3997.4556 SWIFT: VVTBVNVX VIET VICTORY BANK 9th FLOOR, 10 PHO QUANG STREET, WARD 2, TAN BINH DISTRICT, HCM CITY, VIETNAM Tel: 08.3997.4556 SWIFT: VVTBVNVX | Bug | C-Minor | Nghia | 2015-07-03 | 2015-07-03 | Delivered |  | Refer to Import LC
Bug11 | Trade Finance | Thư thông báo | Export/DocumentCredit/Advising LC Ngày tren Thu thong bao: chưa thể hiện => Them field "Created Date" tren Field 20. ----- Them field tren Main va update value on Date: tren thu thong bao | Bug | C-Minor | Nghia | 2015-06-24 | 2015-06-24 | Delivered |  | Add field. But from local site, report is always have issue date.
Bug12 | Trade Finance | Thư thông báo | Canh dòng cho nội dung: "Chúng tôi xin thông báo Ngân hàng phát hành đã phát hành We wish to inform you that the Issuing Bank has issued  Thư tín dụng nêu trên với nội dung như bản đính kèm. The aforesaid Documentary Credit. Please see the enclosure for details � Tu chỉnh theo thư tín dụng nêu trên với nội dung như bản đính kèm. Amendment under the aforesaid Documentary Credit. Please see the enclosure for details Số thứ tự của tu chỉnh: Number of amendment" | Bug | C-Minor | Nghia | 2015-07-03 | 2015-07-03 | Delivered
Bug13 | Trade Finance | Thư thông báo | Logo VietVictoryBank => kich thuoc chua dung (da gui Anh Nguyen logo) | Bug | C-Minor | Nghia | 2015-07-03 | 2015-07-03 | Delivered
Bug14 | Trade Finance | Bia LC | - Canh dong cac noi dung xuat tren bia '- Hang hoa: xuat ten hang hoa sai chinh ta =>lấy theo Field 45A.1 (tab main) | Bug | C-Minor | Nghia | 2015-07-03 | 2015-07-03 | Delivered
Bug15 | Trade Finance | Bia LC | Logo VietVictoryBank => kich thuoc chua dung | Bug |  | Nghia |  |  | Delivered
Bug16 | Trade Finance | TradingFinance/Export/DocumentCredit/AdvisingAndNegotiateLC Phieu VAT | Chua xuat duoc phieu VAT, va chua kiem tra duoc thong tin tren Phieu Chua co in duoc phieu VAT | Bug | B-Major | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | [30-June-2015] The VAT file is exisiting in dev enviroment, just missing on testing site Issue cannot find out the VAT file, so take similar file from another (Import/Document Collection/Register)
Bug17 | Trade Finance | 32B.Increase of Documentary Credit Amount | Export/DocumentCredit/AmendLC theo format Field 32B của Advising LC => đã bổ sung Field này nhưng hệ thống lại bắt buộc nhập mới commit => đề nghị: không bắt buộc nhập ở Field này | Bug | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | Comment the validated AdvisingAndNegotiationLCAmend Revision: 56
Bug18 | Trade Finance | 33B.Decrease of Documentary Credit Amount | Export/DocumentCredit/AmendLC theo format Field 32B của Advising LC => đã bổ sung Field này nhưng hệ thống lại bắt buộc nhập mới commit => đề nghị: không bắt buộc nhập ở Field này | Bug | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | Comment the validated AdvisingAndNegotiationLCAmend Revision: 56
Bug19 | Trade Finance | Thêm Field 'Documentary Credit Number' | Export/DocumentCredit/EnquiryLC khi nhập số LC vào sẽ tra soát ra được reference numer, các giao dịch có liên quan đến số LC đó trên hệ thống | Bug | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | [30-June-2015]: working in dev enviroment. Suggest to publish again file: EnquiryLC.ascx.cs Only issue on testing site Đã thêm Field này nhưng khi nhập số LC vào chạy ra các giao dịch bị lỗi, chưa nhập thông tin Vui lòng cho số LC cụ thể. => Vd: LC-831-705284, so LC nay la so the hien o Field 20 tren tab main do anh. Moi giao dich se co tung so LC khac nhau
Bug20 | Trade Finance | Export/DocumentCredit/EnquiryLC Issue date | Bo sung them dieu kien tim kiem issue date theo dang tu ngay…den ngay… | SCR | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | EnquiryLC Revision: 57
Bug21 | Trade Finance | Issuing Bank | Bo sung them dieu kien tim kiem la Issuing bank No | Bug | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | IssuingBankNo search is working on Dev enviroment, only issue on Testing site Suggest to publish again file: EnquiryLC.ascx.cs Only issue on testing site
Bug22 | Trade Finance | Export/DocumentCredit/EnquiryLC Màn hình tìm kiếm giao dịch | Chức năng Enquiry LC chỉ tìm Advising | Bug | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered |  | Hiện tại, các trường dùng để tìm kiếm còn lại đều không hoạt động, chỉ tra soát được giao dịch LC đã làm khi sử dụng Beneficiary ID 1. Anh Nguyên: Cho 1 ví dụ cụ thể (ISSUING BANK: DIWAJPJT) =>Kiều: y la tim theo dieu kien nao thi ket qua chi hien thi cac giao dich thuoc dieu do Vd: tim theo so LC (documentary Credit Number) thi chi hien ket qua cua giao dich co so LC nay thoi 2. Anh Nguyên: Chức năng Enquiry LC chỉ tìm Advising, để tìm Amend LC thì vào trong Amend, click nút tìm vân vân => DONE
Bug23 | Trade Finance | Export/DocumentCredit/EnquiryLC Màn hình tìm kiếm giao dịch | Thêm Field 'Documentary Credit Number' => khi nhập số LC vào sẽ tra soát ra được reference numer, các giao dịch có liên quan đến số LC đó trên hệ thống | Bug | C-Minor | Nghia | 2015-06-30 | 2015-06-30 | Delivered
Bug24 | Trade Finance | Export/DocumentCredit/CancelLC Tab Main/59.1 Beneficiary Number | Thêm trường này vào trước Field 59.2, droplist danh sách khách hàng và customer ID như đã có trong hệ thống. Đánh dấu * ở tab main (trường bắt buộc nhập, k nhập k cho xử lý giao dịch) (như ở tab 32B) => Done nhưng tab charge vẫn chưa cho phép thu phí | Bug |  | aNguyen |  |  | Closed |  | Will recheck and discuss later
Bug25 | Trade Finance | Export/DocumentCredit/Processing/Register | 1. Other Information: 13.1.4 --> Create 9 empty text box 2. When click on (+) don't generate for 13.1.4 | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | DocumentProcessing
Bug26 | Trade Finance | Export/DocumentCredit/Processing/Register | 14. Remark/SettlementInstruction: undefined when type enter | Bug |  |  | 2015-07-02 | 2015-07-02 | Delivered |  | It was changed from Dev code DocumentProcessing
Bug27 | Trade Finance | Export/DocumentCredit/Processing/Register Tab Charge | Tab commision: loai phi dieu chinh ELCCABLE thanh ELCHANDLE | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | DocumentProcessing
Bug28 | Trade Finance | Export/DocumentCredit/Processing/Register Tab Charge | Charge Acct didn't load information in review case | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered
Bug29 | Trade Finance | Export/DocumentCredit/Processing/Register Tab Charge/Party Charged | Bo sung A, BC | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | DocumentProcessing
Bug30 | Trade Finance | Export/DocumentCredit/Processing/Register VAT | Chua xuat duoc phieu VAT, va chua kiem tra duoc thong tin tren Phieu | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | It is working on Dev site. Will test again with latest one when it is deployed DocumentProcessing
Bug31 | Trade Finance | Export/DocumentCredit/Processing/Register Search | Sửa Ref No. thành LC No. , tuy nhiên dữ liệu lấy tại trường này đã đúng rồi, ko thay đổi dữ liệu | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | EnquiryDocumentProcessing
Bug32 | Trade Finance | Export/DocumentCredit/Processing/Accept Tab Main/59.1 Beneficiary Number | Thêm trường này vào trước Field 59.2, droplist danh sách khách hàng và customer ID như đã có trong hệ thống. Đánh dấu * ở tab main (trường bắt buộc nhập, k nhập k cho xử lý giao dịch) (như ở tab 32B) => Done nhưng tab charge vẫn chưa cho phép thu phí |  |  | aNguyen |  |  | Closed
Bug33 | Trade Finance | Export/DocumentCredit/Processing/Accept Detail | Add: Acceptance Date Maturity Date theo format Field 31C, 31D của Advising LC | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | EnquiryDocumentProcessing
Bug34 | Trade Finance | Export/DocumentCredit/Processing/Accept Remove tab charge |  | Bug | C-Minor | Nghia | 2015-07-02 | 2015-07-02 | Delivered |  | EnquiryDocumentProcessing
Bug35 | Trade Finance | Export/DocumentCredit/Processing SETTLEMENT |  | SCR |  |  |  |  | Delivered |  | New requirement, aNguyen will send detail later
Bug36 | Trade Finance | Export/DocumentCredit/Processing Amend Tab Main/59.1 Beneficiary Number | Tab Main/59.1 Beneficiary Number Thêm trường này vào trước Field 59.2, droplist danh sách khách hàng và customer ID như đã có trong hệ thống. Đánh dấu * ở tab main (trường bắt buộc nhập, k nhập k cho xử lý giao dịch) (như ở tab 32B) | Bug |  | aNguyen |  |  | Delivered |  | Issue was fixed on testing site
Bug37 |  | Export - Documentary Collections - Register Phiếu nhập ngoại bảng | Chỉnh page setup lại cho giống phiếu VAT - Portrait/Landscape (Dung roi khoi sua) -- Align lai so tai Khoan PL -- Check lai total amount | [5 empty] | Fixed |  | Don't see any issue, will recheck on specific LC if it is reported from client again
Bug38 |  | Export - Documentary Collections - Register Format lai Cover | Note: Amount: chinh lai format (ngoai try Yen, VND) 3.2 Collecting Bank Addr. Line1: ten Bank city with swift code | Bug | C-Minor | Nghia | 2015-07-06 | 2015-07-06 | Delivered |  | COVER NHO THU XK.doc trunk_store sql Revision: 63
Bug39 |  |  | it is working | [5 empty] | Closed
Bug40 |  | Export - Documentary Collections - Register Field18: Cho thêm 3 trường nữa để nhập liệu |  | SCR | C-Minor | Nghia | 2015-07-06 | 2015-07-06 | Delivered
Bug41 |  | Export - Documentary Collections - Register Tab Main/Field 3.2 | Cho thêm 1 trường nữa để nhập liệu(Link import LC) | SCR | C-Minor | Nghia | 2015-07-06 | 2015-07-06 | Delivered
Bug42 |  | Export - Documentary Collections - Register Tab Main/Field 4.3 | Cho thêm 1 trường nữa để nhập liệu (-> 4Rows) | SCR | C-Minor | Nghia | 2015-07-06 | 2015-07-06 | Delivered
Bug43 |  | Export - Documentary Collections - Payment | Danh so TT lai | SCR |  |  |  |  | Delivered |  | Revision 66
Bug44 | Trade Finance | Export - Documentary Collections - Payment Credit Acount | . Tài khoản thu chi hộ là tài khoản nội bộ của Ngân hàng, nên tất cả các khách hàng chỉ dùng 1 tài khoản thu chi hộ thôi (ngoại tệ khác thì mới khác tài khoản). Ví dụ: USD123456, EUR123456, SGD123456 tất cả các Khách hàng đều dùng chung tài khoản thu chi hộ . Trường này phải hiển thị 2 tài khoản: Thu chi hộ và Tài khoản thanh toán của Khách hàng (Để báo có trực tiếp vào TK khách hàng hoặc báo có gián tiếp thông qua tài khoản thu chi hộ khi có phát sinh nghiệp vụ chiết khấu BCT) ==> Hệ thống hiện tại chỉ đáp ứng chọn Tk Khách hàng tương ứng Currency; Tk Thu chi hộ tạm thời không đáp ứng trong giai đoạn nà |  |  | aNguyen |  |  | Closed |  | anh Nguyen se check voi client
Bug45 | Trade Finance | Export - Documentary Collections - Payment Tab MT910 | Thêm số thứ tự của Field vào các field như chuẩn Swift (aNguyen se gui thong tin) | Bug |  |  | 2015-10-03 | 2015-10-03 | Fixed |  | [03-10 Hien] - added number as required - confirm a.Nguyen for number at "Address" fill or not fill number
Bug46 | Trade Finance | Export - Documentary Collections - Payment Tab MT910 | Remove field Nostro Account Lay gia tri Currency tu tab Main ==> Not Edit |  |  |  | 2015-09-30 | 2015-09-30 | Fixed |  | [30-Sep Hien] - Disable currency in tab MT910, get value of Currency from tab Main - Hide "Nostro Account" on UI, need to check impact on DB - Remove "Ordering Institution Address 1/2/3" and "intermediary Address 1/2/3" labels
| Trade Finance | Export - Documentary Collections - Payment | Field 4.2 & 4.3: Sua thanh 4.1 & 4.2 ;
|  | Export - Documentary Collections - Payment | Receive Charge: Field Charge Code: Thay thanh "ELC.RECEIVE" Courier Charge: Field Charge Code: Thay thanh "ELC.COURIER" Other Charge: Field Charge Code: Thay thanh "ELC.OTHER" Payment Charge: Field Charge Code: Thay thanh "ELC.PAYMENT"
|  | Export - Documentary Collections - Payment | Field Party Charge: Bo dien giai sau combo box
Bug47 | Trade Finance | Export - Documentary Collections - Payment Tab charge/Party charge | Yêu cầu: - Bo thu phi Oversea Mnus & Plus . - Khong thay doi gia tri amount tab MT910. - Phieu CK: Hien thi gia tri amount MT910 (No Nostro; Co TKKH); Hien thi so tien No Co chinh xac; Dien Giai: Sua "Thanh toan" thanh "Bao co" - Phieu Thu Phi VAT: Thieu TK No; Hien Thi So Tien No Co chinh xac Thieu tai khoan PL cua VAT | Bug | B-Major | Nghia | 2015-09-30 | 2015-10-06 | Fixed |  | [6-10 Hien] Done except VAT NO, Store Procudure's working fine but there's not information stored in DB (table BOUTGOINGCOLLECTIONPAYMENTCHARGES, check with aNguyen to get more information) [04-Oct Hien] - confirmed wih aNguyen, don't need PL for VAT. - Added space between "USD" and value [02-Oct Hien] - Confirm with aNguyen for value of PL account at total VAT. There're many PL accounts, which PL should be shown. [30-Sep Hien] - Hide Oversea Mnus & Plus [7-July-2015] 1. Disable Party Charged, not allow to change 2.Display value of amount (Tab 910) = Drawing Amount (Main) -BB + BC --> lam sau Lưu ý: Phiếu báo có, Nợ tk Nostro tabMain/field 19, Có hoặc tk KH tabMain (Drawer) hoặc tk Thu Chi Hộ Check voi aNguyen vao T2
Bug48 | Trade Finance | Export - Documentary Collections - Payment VAT | . Bị thiếu tài khoản nợ có, . sai số tiền phí, . phần diễn giải nội dung chỉnh lại cho đúng dòng đúng vị trí với nội dung: "Thu phí báo có DP TF...". Phần diễn giải đang lấy nhầm loại hình, nhờ thu DA nhưng lại hiển thị DP | Bug | B-Major | Nghia | 2015-07-09 | 2015-07-09 | Fixed
|  | Export - Documentary Collections - Payment | Khong xuat Phieu Xuat Ngoai Bang | Bug | B-Major
Bug49 | Trade Finance | Export - Documentary Collections - Payment Phiếu chuyển khoản | - Thay doi Transfer Slip thanh "Phieu Chuyen Khoan". Tat Ca - Ap dung cong thuc Thu Phi Bug47 | Bug | C-Minor | Nguyen | 2015-09-30 | 2015-09-30 | Fixed |  | [30-Sep Hien] - Changed "Transfer Slip" to "Phieu Chuyen Khoan"
Bug50 | Trade Finance | Export - Documentary Collections - Payment Phiếu xuất ngoại bảng | - Khong in duoc | Bug |  |  | 2015-09-30 | 2015-10-06 | Fixed |  | [6-Oct Hien] Done [02-Oct Hien] - Report file is exported - Gettting data from DB to fill in export file (Ongoing) [30-Sep Hien] - Add function to report Phieu Xuat Ngoai Bang - Check for template of Phieu Xuat Ngoai Bang with a.Nguyen
Bug51 | Credit | Product Limit: Approved Date,Offered ,Until Date, Expiry Date, Proposal Date | - Neu han muc con chua ton tai, lay cac gia tri nay cua han muc Cha - Ngc lai, Neu han muc con ton tai, lay cac gia tri nay cua han muc con - Ktra gia tri cua tung field ngay phai <= gia tri field ngay tuong ung cua han muc Cha | Bug | B-Major | Nghia | 2015-07-13 | 2014-07-13 | Fixed |  | Revison: 110
Bug52 | Credit | Enquiry Global Limit - Hien thi gia tri cho 2 field Maximum Secured va Maximum UnSecured |  | Bug | C-Minor | Nghia | 2015-07-16 | 2015-07-16 | Fixed |  | DefineCustomerLimit
Bug53 | Credit | Khi nhan Enter tai field Product Limit No, van hien thi gia tri cho 2 fields Customer ID & Product Limit |  | Bug | C-Minor | Nghia | 2015-07-16 | 2015-07-16 | Fixed |  | DefineCustomerLimitSub
Bug54 | Credit | Collateral Information - Collateral Type: Remove gia tri “900 – Tin Chap” - Field Currency – Them gia tri “Vang” sau VND |  | SCR | C-Minor | Nghia | 2015-07-16 | 2015-07-16 | Fixed
Bug55 | Credit | Input Loan Contract: | - Tab Other Info: Field Collateral Amount: Format cho phep nhap ‘b’ the hien gia tri tien Ty. - Truong hop giai ngan nhieu lan: Trong tab Disbursal Schedule: Khi commit, Kiem tra gia tri field Drawdown Date, neu field nay co gia tri > ngay System Date thi bao loi “…” | SCR | C-Minor | Nghia | 2015-07-16 | 2015-07-16 | Fixed
Bug56 | Credit | Input Contingent Entry: Sauk hi nhap ID cua tai san dam bao (CIF.01), kiem tra logic load thong tin len man hinh nay. |  | Bug |  |  |  |  | On-Hold |  | Need to know what is wrong from Customer so that we can check propertly
Bug57 | Credit | Xac nhan gia tri 2 field Ngay trong Lich Tra No: - Ngay duoi Title Lich Tra No: Lay gia tri field Value Date - Ngay Ky: Lay gia tri field Value Date |  | Bug | C-Minor | Nghia | 2015-07-16 | 2015-07-16 | Fixed |  | LichTraNoHopDongVayRepayment.docx LichTraNoHopDongVay.docx NewNormalLoan
Bug58 | Credit | Hieu chinh logic tinh lai + von, in lich tra no cho truong hop Hop Dong Vay lai suat tha noi | Vi du: - 2 Thang dau  Lai suat 5% - Tu thang thu 3  Lai suat Tiet Kiem 13T + Bien do 2% - 6 thang ap ung thay doi Lai suat Tiet Kiem 13T mot lan | Bug | B-Major | Nghia | 2015-07-20 | 2015-07-20 | Fixed
Bug59 | Credit | Hide chuc nang Repayment Schedule |  | SCR | C-Minor | aNguyen |  |  | Not Start |  | It can be hihen from DNN configuration
Bug60 | Trade Finance | Export - Documentary Collections - Register Phiếu VAT (Lay NoiDung la field 18, Khong dung) | Đang lấy nhầm trường 18 tab main  Đề nghị ko hiển thị dữ liệu |  | C-Minor | Nghia | 2015-07-30 | 2015-07-30 | Fixed |  | Khong hien thi cho field NoiDung trong VAT
Bug61 | Trade Finance | (Export - Documentary Collections - Register) In phiếu VAT Noi dung ko dung | Field Noi Dung: Lay gia tri field Charge Remark trong man hinh tab Charge |  |  |  | 2015-10-06 |  | Fixed |  | [06-Oct Hien] Ongoing, will be done by today [30-July-2015]BIS- Hien tai Accept va Register su dung chung function, chung VAT document template. [28-July-2015] [BIS] Raised Bug61 to chek
Bug62 | Trade Finance | TẠO MỚI NHỜ THU (Export - Documentary Collections - Register) BÁO CÓ NHỜ THU XUẤT (Payments) Tab Main/1.1 Draw Type | Dựa vào số TF để xác định đó là SP hay MA, sau khi gõ số TF thì trường này tự động lấy giá trị SP/MA tương ứng - Neu Register la DP thi Payment la SP; Nguoc lai la MA; |  |  |  | 2015-10-02 | 2015-10-02 | Fixed |  | [02-Oct Hien] Done [28-July-2015][BIS] Raised Bug62 to check. Anh Nguyen check lai dum, day co phai la new Requirement?
Bug63 | Trade Finance | Tab charge/Overseas plus charge, oversea minus charge | Field Charge Account: không hiển thị giá trị nào hết. Lý do: 2 sub-tab charge này tương ứng với 2 mã phí BB, BC. Mà 2 mã phí này không thu từ tài khoản khách hàng, mã phí này là căn cứ để tính số tiền báo có trên phiếu chuyển khoản báo có mà thôi |  | C-Minor | Nghia | 2015-07-30 | 2015-07-30 | Fixed
Bug64 | Trade Finance | Tab charge/Overseas plus charge, oversea minus charge | Như đã trao đổi trước đây, mã phí BB, BC không tính VAT. Lỗi hiện nay vẫn tính VAT --> Đề nghị không tính VAT |  | C-Minor |  |  |  | Closed |  | [Nghia] anh Nguyen check lai loi nay dum em, hien tai minh cung ko tinh VAT cho BB va BC, voi lai tren testing site, Party Charged van con enable, no nen read only.
Bug 65 | Trade Finance | BÁO CÓ NHỜ THU XUẤT (Export/Documentary Collections/Payments) - Tab Main | Remove field 1.6 Payment Method | SCR | B-Major |  | 2015-10-03 | 2015-10-03 | Fixed |  | [03-Oct Hien] Done [1-10 Hien] - Removed filed
Bug 66 | Trade Finance | BÁO CÓ NHỜ THU XUẤT (Export/Documentary Collections/Payments) - Tab Main | Remove field 1.10 Exchange Rate | SCR | B-Major |  | 2015-10-03 | 2015-10-03 | Fixed |  | [03-Oct Hien] - Removed filed - Confirm with aNguyen for formual which is used to calculate drFromAmmount
Bug 67 | Trade Finance | Export Documentary Credit/Advising LC Gia tri: - ELCA - Export LC Acceptance- 70001 - ELCD - Export LC Deffered - 70002 - ELCM - Export LC Mixed Payment - 70003 - ELCP - Export LC Payment - 70004 - ELCS - Export LC Negotiatable Sight - 70005 - ELCU - Export LC Negotiable Usance - 70006 | Them field Drop box LC Type (*) duoi field Create Date. | SCR | B-Major |  |  |  | Fixed |  | [09-Oct Hien] Done [06-Oct Hien] Ongoing, will try to finish by tomorrow
Bug 68 | Trade Finance | Export Documentary Processing/Settlement | Xay dung man hinh GIONG Y CHANG man hinh Export Collection/Payment. Ngoai tru mot so khac biet ben duoi. Chi mot man hinh Settlement (khong tach ra 2 man hinh nhu hien tai)
Bug | Trade Finance | Export Documentary Processing/Settlement Tab Main/1.1 Draw Type | Dựa vào số TF để xác định đó là SP hay MA, sau khi gõ số TF thì trường này tự động lấy giá trị SP/MA tương ứng - Neu Adising LC/LC Type la (ELCM,ELCP,ELCS) la SP - Neu Adising LC/LC Type la (ELCA,ELCD,ELCU) la MA | SCR | B-Major |  |  |  | New
Bug | Trade Finance | Export Documentary Processing/Settlement Tab Main/1.6 | Remove field 1.6 Payment Method | SCR | B-Major |  |  |  | Fixed
Bug | Trade Finance | Export Documentary Processing/Settlement Tab Main/1.10 | Remove field 1.10 Exchange Rate | SCR | B-Major |  |  |  | Fixed
| Trade Finance | Export Documentary Processing/Settlement Tab Main/1.12 | Remove duplicate label | Bug | C-Minor |  |  |  | Fixed
|  | Export Documentary Processing/Settlement Tab Main/ | Sua title Drawer Information thanh "Beneficiary Information" Field 2.1: Sua "Collection" thanh "LC"; Gia tri mac dinh GIONG field "LC Type" trong man hinh Export Credit/Advising LC Field 2.2,2.3 & 2.4: Remove "Drawer"; Viet ro "Customer" thay vi "Cus"
|  | Export Documentary Processing/Settlement Tab Main/ | Sua title Collecting Bank Detail thanh "Presenting Bank Details" Field 3.1 & 3.2: Bo chu Collecting | [5 empty] | Fixed
|  | Export Documentary Processing/Settlement Tab Main/ | Sua Drawee/Reimbursement Detail thanh "Applicant Details" Field 4.2 & 4.3: Sua thanh 4.1 & 4.2 ; Bo chu Drawee | [5 empty] | Fixed
|  | Export Documentary Processing/Settlement Tab Main/ | Sua title Collection Information thanh "Setttlement Information" | [5 empty] | Fixed
|  | Export Documentary Processing/Settlement Tab Charge/ | Receive Charge: Field Charge Code: Thay thanh "ELC.RECEIVE" Courier Charge: Field Charge Code: Thay thanh "ELC.COURIER" Other Charge: Field Charge Code: Thay thanh "ELC.OTHER" Payment Charge: Field Charge Code: Thay thanh "ELC.PAYMENT"
|  | Export Documentary Processing/Settlement Tab Charge/ | Field Party Charge: Bo dien giai sau combo box | [5 empty] | Fixed
| Trade Finance | Import Documentary Collection/Accept Số tiền bằng chữ | Lưu ý check lại số tiền bằng chữ ở các phiếu, hóa đơn (vd: EUR thì ko có chữ "đồng"…) | Bug | C-Minor |  |  |  | Lưu ý check lại số tiền bằng chữ ở các phiếu, hóa đơn (vd: EUR thì ko có chữ "đồng"…) | New arise | Tất cả các lỗi này đã email Anh Nguyên trước đây
| Trade Finance | Import Documentary Collection/Accept MT412 | ngày maturity date xuat file điện 412 không đúng (hiện tại field này lấy ngày khai báo giao dịch thay vì lấy ngày maturity mới đúng) | Bug | B-Major |  |  |  | ngày maturity date xuat file điện 412 không đúng (hiện tại field này lấy ngày khai báo giao dịch thay vì lấy ngày maturity mới đúng) | New arise
| Trade Finance | Import Documentary Collection/Accept Tab MT412 | Them field 32. Maturity Date tren field Currency theo dung format dien Swift Maturity: Lay gia tri tu tab Main field 8 . Cho phep chinh sua Dien MT412: Lay gia tri Maturity Date tren man hinh tab MT412 | Bug | B-Major |  |  |  | Them field 32. Maturity Date tren field Currency theo dung format dien Swift Maturity: Lay gia tri tu tab Main field 8 . Cho phep chinh sua Dien MT412: Lay gia tri Maturity Date tren man hinh tab MT412 | Bug
| Trade Finance | Tab MT412 | Tu dong lay gia tri tab Main | Bug | B-Major |  |  |  | Tu dong lay gia tri tab Main | Bug
|  | Export Collection/Register | Thay doi page setup thanh Landscap. Dong nhat format | Bug | B-Major | Nguyen
| Trade Finance | Export Collection/Register | Tab Charge: Charge Account khong refesh data khi thay doi dong tien USD, EUR & VND - Check lai logic filter: Khi thay doi Customer Name ben tab Main ==> Issue nay xuat hien | Bug | B-Major
| Trade Finance | Export Collection/Accept | Check lai data cho Phieu Thu Phi VAT - Sai so tien Thu Phi Make sure: Noi Dung lay tu Charge Remark tren tab Charge | Bug | B-Major
| Trade Finance | Load them day du gia tri Country |  | Bug | B-Major | Nguyen
|  | Export Collection/Payment | Tab Main: Nhap so TF, tu dong load gia tri Currency da nhap tu man hinh Register | Bug | B-Major |  |  |  | Tu dong lay gia tri tab Main
|  | Export Collection/Payment | VAT: Hien thi so tien khong dung. | Bug | B-Major
Cac Chuc Nang Export Credit hien tai chua test ky. Supposed se con nhieu bugs
,

## Data
Severity | Status | Type | Category
A-Critical | New | Bug | Trade Finance
B-Major | On-Going | SCR | Credit
C-Minor | Fixed |  | Transfer
| Delivered |  | Teller
| Closed |  | Treasury
| Not Reproducible |  | Report
Not Start
On-Hold
Partial Fixed